## Batman
Virtual Stock
Batman
| Project Lead: |  | Mengyuan Zhu
| Project Start Date: |  | 2017-01-21 | time axis 2017-01-16 to 2017-04-16
| Display Week: |  | 1 |  |  |  |  | 2017-01-16: Week 1; 2017-01-23: Week 2; 2017-01-30: Week 3; 2017-02-06: Week 4; 2017-02-13: Week 5; 2017-02-20: Week 6; 2017-02-27: Week 7; 2017-03-06: Week 8; 2017-03-13: Week 9; 2017-03-20: Week 10; 2017-03-27: Week 11; 2017-04-03: Week 12; 2017-04-10: Week 13
[8 empty] | 2017-01-16 | [6 empty] | 2017-01-23 | [6 empty] | 2017-01-30 | [6 empty] | 2017-02-06 | [6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10
WBS | Task | Lead | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Introduction
1.1 | Title Page | Mengyuan | 2017-01-21 | 2017-01-21 | 1 | 100% | 1
1.2 | Resumes |  | 2017-01-22 | 2017-01-22 | 1 | 100% | 1
1.3 | Approved topic |  | 2017-01-23 | 2017-01-23 | 1 | 100% | 1
1.4 | Work Strucutere Document |  | 2017-01-22 | 2017-01-23 | 2 | 100% | 1
2 | Requirements Elicitation
2.1 | Problem statement | Mengyaun | 2017-01-26 |  | 1 | 0% | 0
2.2 | Requirements Traceabillity Matrix | Jakub | 2017-01-26 |  | 1 | 0% | 0
2.3 | Gantt Chart | Sungjae | 2017-01-26 | 2017-01-26 | 1 | 100% | 1
2.4 | Dictionary | Hyeun | 2017-01-26 |  | 1 | 0% | 1
2.5 | Topic rational | Sharon | 2017-01-26 |  | 1 | 0% | 1
2.6 | Updated WSD | Mengyaun | 2017-01-26 |  | 1 | 0% | 1
3 | System Analysis & Design
3.1 | Horizontal prototype |  |  |  | 1 | 0% | 0
3.2 | RTM Update | Jakub |  |  | 1 | 0% | 0
3.3 | Use cases & Interaction Diagram |  |  |  | 1 | 0% | 0
3.4 | Function Point Cost Analysis |  |  |  | 1 | 0% | 0
3.5 | Updated WSD | Mengyaun |  |  | 1 | 0% | 0
3.6 | Updated Gantt Chart | Sungjae |  |  | 1 | 0% | 0
3.7 | Dictionary | Hyeun |  |  | 1 | 0% | 0
3.8 | Use cases rational | Sharon |  |  | 1 | 0% | 0
4 | Object Design
4.1 | Software architecture used |  |  |  | 1 | 0% | 0
4.2 | RTM Update | Jakub |  |  | 1 | 0% | 0
4.3 | Category Interaction Diagram |  |  |  | 1 | 0% | 0
4.4 | Design of objects |  |  |  | 1 | 0% | 0
4.5 | Updated WSD | Mengyaun |  |  | 1 | 0% | 0
4.6 | Updated Gantt Chart | Sungjae |  |  | 1 | 0% | 0
4.7 | Dictionary | Hyeun |  |  | 1 | 0% | 0
4.8 | Object design rational | Sharon |  |  | 1 | 0% | 0
5 | Rationale
5.1 | Merge rationale | Sharon |  |  | 1 | 0% | 0
5.2 | RTM Update | Jakub |  |  | 1 | 0% | 0
5.3 | Updated WSD | Mengyaun |  |  | 1 | 0% | 0
5.4 | Updated Gantt Chart | Sungjae |  |  | 1 | 0% | 0
5.5 | Dictionary | Hyeun |  |  | 1 | 0% | 0
6 | Test Document & Code
6.1 | RTM Update | Jakub |  |  | 1 | 0% | 0
6.2 | Source code & Executable code |  |  |  | 1 | 0% | 0
6.3 | Test cases |  |  |  | 1 | 0% | 0
6.4 | Updated WSD | Mengyaun |  |  | 1 | 0% | 0
6.5 | Updated Gantt Chart | Sungjae |  |  | 1 | 0% | 0
6.6 | Dictionary | Hyeun |  |  | 1 | 0% | 0
6.7 | Test cases rational | Sharon |  |  | 1 | 0% | 0
6.8 | COCOMO
7 | Final Report
7.1 | Table of Contents |  |  |  | 1 | 0% | 0
7.2 | Full documentation |  |  |  | 1 | 0% | 0
7.3 | Function Point Cost Analysis & COCOMO |  |  |  | 1 | 0% | 0
7.4 | Prototype |  |  |  | 1 | 0% | 0
7.5 | Project legacy |  |  |  | 1 | 0% | 0
7.6 | Final WSD | Mengyaun |  |  | 1 | 0% | 0
7.7 | Final Gantt Chart | Sungjae |  |  | 1 | 0% | 0
7.8 | Dictionary | Hyeun |  |  | 1 | 0% | 0
7.9 | Resumes |  |  |  | 1 | 0% | 0
7.10.1 | User Guide |  |  |  | 1 | 0% | 0
7.10.2 | Email from GIT |  |  |  | 1 | 0% | 0
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on G7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.